## Sheet1
System Name | CITU-Connect
Members:
A - | Bacarisas, John Clyde H.
B - | Ligan, Michael Andre B.
C - | Perolino, Sherween R.
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 1
1.1. Create Functional Requirements Document |  | 08/28/24 | 08/30/24 | Done
1.2. Create Gantt Chart |  | 08/28/24 | 09/23/24 | Done
Phase 2
2.1. Create GitHub Repository |  | 09/23/24 | 09/23/24 | Done
2.2. Commit FRD and Gantt Chart |  | 09/23/24 | 09/23/24 | Done
Phase 3
3.1. Assign Functionalities |  | 09/23/24 | 09/23/24 | Done
3.2. Create ERD using Visual Paradigm |  | 09/23/24 | 09/23/24 | Done
3.3. Commit ERD |  | 09/23/24 | 09/23/24 | Done
3.4. Commit UI/UX Design (for each member) |  | 09/23/24 | 09/23/24 | Done
Functional Requirements Implementation
1. User Athentication |  |  |  | Todo
1.1. LOG IN | A |  |  | Todo
1.2. Creating UI | A |  |  | Todo
1.3. Integrate with DB | A |  |  | Todo
1.4. LOG OUT | A |  |  | Todo
2. Data Management (CRUD)
2.1. Create | A |  |  | Todo
2.2. Read | B |  |  | Todo
2.3. Update | C |  |  | Todo
2.4 Delete | A |  |  | Todo
2.5. Create UI | B |  |  | Todo
3. User Interface
3.1. Figma Designing | B |  |  | Todo
3.2. Wireframe Prototyping | B |  |  | Todo
3.3. Front-end Development | C |  |  | Todo
4. Notification System
4.1. Define Notification Types (email, SMS, in-app) | C |  |  | Todo
4.2. Set Notification Preferences | C |  |  | Todo
4.3. Implement Notification preferences | C |  |  | Todo

## Sheet2
System Name | CITU-Connect
Members:
A - | Bacarisas, John Clyde H.
B - | Ligan, Michael Andre B.
C - | Perolino, Sherween R.
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 1
1.1. Create